## Gap Analysis
Gap Analysis — ShopNest Inc. ¦ Oracle Fusion Cloud SCM Implementation
Inventory & Procurement Module ¦ Prepared for: ShopNest Inc. ¦ Date: March 2026
Area | AS-IS (Current State) | TO-BE (Oracle Fusion) | Oracle Module | Priority | Est. Benefit
INVENTORY MANAGEMENT
Inventory visibility | Manual spreadsheets per warehouse. No real-time view across NY, CHI, LA. | Single real-time dashboard showing stock across all 3 warehouses. | Oracle Inventory Mgmt | High | Eliminate ~8 hrs/week manual updates
Reorder automation | Manual reorder decisions. Frequent stockouts and overstocking. | Automated reorder point triggers. Purchase requisition auto-created on breach. | Oracle Inventory Mgmt | High | Reduce stockouts by est. 60%
PROCUREMENT
Purchase orders | POs raised manually via email. No standard template or audit trail. | Structured PO creation with approval workflow and full audit log. | Oracle Purchasing | High | Full compliance & audit trail
Supplier management | No central supplier database. Duplicate vendors. No performance tracking. | Centralized supplier registry with scorecards and portal access. | Oracle Supplier Portal | Medium | Reduce duplicate vendors by 100%
FINANCE & COMPLIANCE
Invoice matching | Manual invoice verification. Errors cause overpayments or delays. | Automated 3-way match (PO + GRN + Invoice). Exceptions flagged only. | Oracle Payables | Medium | Reduce payment errors by est. 80%
Reporting & analytics | Ad-hoc Excel reports. No standard KPIs or procurement dashboards. | Pre-built SCM dashboards. Procurement spend analytics via Oracle OAC. | Oracle OAC | Low | Real-time exec visibility

## Implementation Plan
Oracle Fusion SCM — 6-Month Implementation Plan ¦ ShopNest Inc.
Phased rollout across 3 warehouses: New York ¦ Chicago ¦ Los Angeles
Phase | Duration | Scope | Oracle Modules | Success Criteria
Phase 1 Foundation | Months 1–2 | • Real-time inventory across 3 warehouses • Automated reorder point triggers • Structured PO creation & approval workflow • User training — warehouse & procurement teams | • Oracle Inventory Management • Oracle Purchasing • Oracle Approvals Management | • Live inventory dashboard operational • Zero manual POs via email • Reorder automation active for top 100 SKUs
Phase 2 Procurement | Months 3–4 | • Supplier portal go-live • Centralized vendor registry (deduplicated) • Automated 3-way match (PO+GRN+Invoice) • AP payment automation | • Oracle Supplier Portal • Oracle Payables • Oracle AP Automation | • All suppliers onboarded to portal • 3-way match auto-processing >90% invoices • Payment error rate <2%
Phase 3 Analytics | Months 5–6 | • Procurement spend dashboards • KPI reporting (fill rate, PO cycle time, supplier OTD) • Management reporting templates • Post-go-live optimization & UAT sign-off | • Oracle Analytics Cloud (OAC) • Oracle SCM Reporting • Oracle BI Publisher | • Executive dashboard live • All KPIs tracked & baselined • Full UAT sign-off completed

## KPI Tracker
ShopNest Inc. — ERP KPI Tracker (Post-Implementation)
KPI | Baseline (AS-IS) | Target (TO-BE) | Month 3 Actual | Month 6 Actual | Status
Stockout rate | 12% | <5% | 7% | 4% | On Track
PO processing time | 5 days | <1 day | 2 days | 0.5 days | On Track
Invoice match rate (auto) | 0% | >90% | 65% | 93% | On Track
Duplicate supplier records | 34 | 0 | 8 | 0 | Achieved
Inventory accuracy | 72% | >98% | 89% | 99% | Achieved
Procurement cost reduction | 0% | 18–24% | 9% | 21% | On Track

## Tableau_Inventory
Item_Name | SKU | Category | Warehouse | Quantity_On_Hand | Quantity_Reserved | Available_Stock | Reorder_Point | Stock_Status | Unit_Price | Inventory_Value
Laptop 15" | SKU-1001 | Electronics | New York | 45 | 5 | 40 | 50 | BELOW REORDER POINT | 850 | 38250
Laptop 15" | SKU-1001 | Electronics | Chicago | 30 | 2 | 28 | 50 | BELOW REORDER POINT | 850 | 25500
Laptop 15" | SKU-1001 | Electronics | Los Angeles | 60 | 0 | 60 | 50 | OK | 850 | 51000
Wireless Mouse | SKU-1002 | Accessories | New York | 180 | 20 | 160 | 200 | BELOW REORDER POINT | 25 | 4500
Wireless Mouse | SKU-1002 | Accessories | Chicago | 90 | 10 | 80 | 200 | BELOW REORDER POINT | 25 | 2250
USB-C Hub | SKU-1003 | Accessories | New York | 120 | 15 | 105 | 150 | BELOW REORDER POINT | 45 | 5400
USB-C Hub | SKU-1003 | Accessories | Chicago | 40 | 5 | 35 | 150 | BELOW REORDER POINT | 45 | 1800
Monitor 27" | SKU-1004 | Electronics | New York | 22 | 3 | 19 | 30 | BELOW REORDER POINT | 400 | 8800
Monitor 27" | SKU-1004 | Electronics | Los Angeles | 18 | 2 | 16 | 30 | BELOW REORDER POINT | 400 | 7200
Mechanical Keyboard | SKU-1005 | Accessories | New York | 85 | 10 | 75 | 100 | LOW STOCK | 95 | 8075
Webcam HD | SKU-1006 | Electronics | Chicago | 55 | 5 | 50 | 80 | LOW STOCK | 75 | 4125
Office Chair | SKU-1007 | Furniture | Los Angeles | 12 | 2 | 10 | 20 | BELOW REORDER POINT | 250 | 3000
Standing Desk | SKU-1008 | Furniture | Los Angeles | 8 | 1 | 7 | 10 | BELOW REORDER POINT | 550 | 4400

## Tableau_Supplier_Spend
Supplier_Name | Country | Payment_Terms | Status | Total_Orders | Total_Spend | Avg_Order_Value | Largest_Order | Spend_Pct_of_Total | Spend_Rank
TechSource Global | USA | NET30 | Active | 2 | 51000 | 25500 | 42500 | 38.5 | 1
ElectroHub Asia | China | NET45 | Active | 2 | 49950 | 24975 | 31200 | 37.7 | 2
PrimeGoods Ltd | India | NET30 | Active | 2 | 22100 | 11050 | 12300 | 16.7 | 3
FastParts Co | USA | NET15 | Active | 2 | 20350 | 10175 | 15600 | 15.4 | 4
GlobalSupply Inc | Germany | NET60 | Inactive | 0 | 0 | 0 | 0 | 0 | 5

## Tableau_PO_Trend
PO_ID | Supplier_Name | PO_Date | Order_Month | Status | Total_Amount | Days_Outstanding | Aging_Bucket
1001 | TechSource Global | 2026-02-25 | Feb-2026 | Completed | 42500 | 30 | 16-30 days
1002 | ElectroHub Asia | 2026-03-07 | Mar-2026 | Completed | 18750 | 20 | 16-30 days
1003 | PrimeGoods Ltd | 2026-03-17 | Mar-2026 | Approved | 12300 | 10 | 0-15 days
1004 | TechSource Global | 2026-03-22 | Mar-2026 | Pending | 8500 | 5 | 0-15 days
1005 | FastParts Co | 2026-03-25 | Mar-2026 | Pending | 4750 | 2 | 0-15 days
1006 | ElectroHub Asia | 2026-02-10 | Feb-2026 | Completed | 31200 | 45 | 31-45 days
1007 | PrimeGoods Ltd | 2026-03-12 | Mar-2026 | Approved | 9800 | 15 | 0-15 days
1008 | FastParts Co | 2026-01-26 | Jan-2026 | Completed | 15600 | 60 | 46-60 days

## Tableau_Category_Spend
Category | Item_Name | SKU | Total_Qty_Ordered | Total_Spend | Pct_of_Total | Spend_Rank
Electronics | Laptop 15" | SKU-1001 | 40 | 34000 | 25.6 | 1
Electronics | Monitor 27" | SKU-1004 | 90 | 32000 | 24.1 | 2
Accessories | Wireless Mouse | SKU-1002 | 700 | 17500 | 13.2 | 3
Accessories | USB-C Hub | SKU-1003 | 400 | 13500 | 10.2 | 4
Furniture | Standing Desk | SKU-1008 | 10 | 5500 | 4.1 | 5
Accessories | Mechanical Keyboard | SKU-1005 | 100 | 9500 | 7.2 | 6
Electronics | Webcam HD | SKU-1006 | 60 | 4500 | 3.4 | 7
Furniture | Office Chair | SKU-1007 | 10 | 2500 | 1.9 | 8